## Communication Plan
PROJECT COMMUNICATION PLAN
Project: | [Project Name] |  | PM: | [PM Name] |  | Prepared: | [Date] | Version: | 1.0
COM ID | Audience (STK-XXX) | Purpose / Message | Channel | Frequency | Format / Template | Owner | Audience Preference | Next Date | Status
COM-001 | Project Sponsor (STK-001) | Report project position, request decisions, flag escalations | Meeting | Monthly | Status Report + Dashboard | PM | Prefers verbal + written; send report 48h before | [Date] | Active
COM-002 | Steering Committee (STK-002, STK-003) | Governance update — RAG, milestones, budget, key risks | Meeting | Monthly | Steering Pack (slides + dashboard) | PM | Send pack 48h before; 30 min slot | [Date] | Active
COM-003 | Project Team (All members) | Weekly priorities, blockers, actions | Meeting | Weekly | Team stand-up (verbal) | PM | Keep to 30 min; use action tracker | [Date] | Active
COM-004 | Finance Director (STK-005) | Monthly budget position — spend, variance, forecast | Report | Monthly | Budget Variance Report | PM | Email PDF; copy to Finance PA | [Date] | Active
COM-005 | All Staff (End Users) | Project awareness, upcoming changes, training schedule | Newsletter | Monthly | Email newsletter | Change Manager | Plain English; no jargon; no attachments | [Date] | Active
COM-006 | IT Department (STK-007) | Technical integration updates, environment readiness | Meeting | Weekly | Technical meeting minutes | Tech Lead | Include BA; share agenda 24h before | [Date] | Active
COM-007 | Vendor / Supplier (STK-010) | Delivery progress, issues, contract milestones | Meeting | Weekly | Vendor meeting minutes | PM | Formal minutes required for contract | [Date] | Active
COM-008 | All Stakeholders | Phase gate completion, upcoming phase, key dates | Email | At Milestone | Milestone announcement email | PM | Send same day as milestone approval | [Date] | Active
COM-009 | [8 empty] | Active
COM-010 | [8 empty] | Active
COM-011 | [8 empty] | Active
COM-012 | [8 empty] | Active
COM-013 | [8 empty] | Active
COM-014 | [8 empty] | Active
COM-015 | [8 empty] | Active
COM-016 | [8 empty] | Active
COM-017 | [8 empty] | Active
COM-018 | [8 empty] | Active
COM-019 | [8 empty] | Active
COM-020 | [8 empty] | Active
COM-021 | [8 empty] | Active
COM-022 | [8 empty] | Active
COM-023 | [8 empty] | Active
COM-024 | [8 empty] | Active
COM-025 | [8 empty] | Active
COM-026 | [8 empty] | Active
COM-027 | [8 empty] | Active
COM-028 | [8 empty] | Active
COM-029 | [8 empty] | Active
COM-030 | [8 empty] | Active
INSTRUCTIONS: One row per communication type. Reference stakeholder STK-IDs from the Stakeholder Register. Update Next Date after each communication is sent. Review and update at each project phase gate.

## Guidance
COMMUNICATION PLAN — FIELD GUIDANCE
COM ID | Pre-filled COM-001 to COM-030. Reference in project schedule for communication activities.
Audience | Named individual(s) or group. Use STK-XXX IDs from the Stakeholder Register for traceability.
Purpose / Message | What the audience should know, decide or do after receiving this communication. Not the document title — the intended outcome.
Channel | Select from drop-down: Email / Meeting / Report / Dashboard / Presentation / One-to-one / Newsletter / Teams/Slack / Other
Frequency | Select from drop-down: Weekly / Fortnightly / Monthly / Quarterly / At Milestone / Ad Hoc / One-off
Format / Template | The specific document or format used — e.g. 'Status Report template', 'Dashboard', 'Verbal briefing', 'Email'.
Owner | Single named person responsible for preparing and sending this communication. One name = one accountability.
Audience Preference | Known preferences from the Stakeholder Register — preferred channel, timing, format, distribution list.
Next Date | Date of the next planned communication. Update after every communication is sent. All past dates = plan not being maintained.
Status | Active = current. On Hold = paused. Completed = one-off done. Cancelled = no longer needed.
KEY PRINCIPLES
One row per comms type | A stakeholder receiving a monthly report AND a weekly meeting = two rows, not one.
Match to stakeholder strategy | Every stakeholder in the register with 'Manage closely' strategy should have at least one weekly communication row.
Review at phase gates | Update audience, frequency and format as stakeholder needs change through the project lifecycle.
Channel matters | The right message through the wrong channel is still the wrong communication. Match channel to stakeholder preference.