## Gantt Chart
PROJECT GANTT CHART
Project: | [Project Name] | PM: | [PM Name] | Start Date: | [Date] | Status Date: | [Date]
ID | Task / Phase Name | Type | Owner | Start Week | Duration (weeks) | % Complete | Predecessor | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
P-1 | 1.0 INITIATION | Phase
T-01 | Project Charter | Task | PM | 1 | 1 | 100% | bar: W1
T-02 | Stakeholder Register | Task | PM | 1 | 2 | 100% | bar: W1 to W2
M-01 | ◆ Initiation Complete | Milestone |  | 2 | 0 | 100% | T-02 | bar: W2
P-2 | 2.0 PLANNING | Phase
T-03 | WBS | Task | PM | 3 | 1 | 100% | M-01 | bar: W3
T-04 | Risk Register | Task | PM | 3 | 2 | 80% | T-03 | bar: W3 to W4
T-05 | Resource Plan | Task | PM | 4 | 2 | 60% | T-03 | bar: W4 to W5
T-06 | Communication Plan | Task | PM | 5 | 1 | 50% | T-04 | bar: W5
M-02 | ◆ Planning Baselined | Milestone |  | 6 | 0 | 0% | T-06 | bar: W6
P-3 | 3.0 EXECUTION | Phase
T-07 | Development Sprint 1 | Task | Dev Lead | 7 | 2 | 100% | M-02 | bar: W7 to W8
T-08 | Development Sprint 2 | Task | Dev Lead | 9 | 2 | 40% | T-07 | bar: W9 to W10
T-09 | Integration Testing | Task | Test Lead | 9 | 2 | 0% | T-07 | bar: W9 to W10
T-10 | UAT Preparation | Task | BA | 10 | 1 | 0% | T-08 | bar: W10
P-4 | 4.0 MONITORING | Phase
T-11 | Weekly Status Reports | Task | PM | 1 | 12 | 60%
T-12 | Steering Committee | Task | PM | 4 | 8 | 50% | bar: W4 to W11
P-5 | 5.0 CLOSURE | Phase
T-13 | UAT Sign-Off | Task | PM | 11 | 1 | 0% | T-09 | bar: W11
T-14 | Handover Document | Task | PM | 11 | 1 | 0% | T-13 | bar: W11
T-15 | Lessons Learned | Task | PM | 12 | 1 | 0% | T-13 | bar: W12
M-03 | ◆ Project Closed | Milestone |  | 12 | 0 | 0% | T-15 | bar: W12
LEGEND: ■ Completed (green) ■ In Progress (violet) ◆ Milestone (amber) ■ Phase (navy) Update % Complete column to reflect actual progress each reporting period.