## RACI Matrix
RACI MATRIX — ROLES & RESPONSIBILITIES
Project: [Project Name] PM: [Name, PMP] Version: 1.0 Date: [DD MMM YYYY]
RACI KEY |  | R = Responsible |  |  | A = Accountable |  |  | C = Consulted |  |  | I = Informed
⚠ Rules: Each task must have exactly ONE Accountable (A). Every task must have at least one Responsible (R). No task should be left blank — if unsure, use Informed (I).
|  | Initiation |  |  | Planning |  |  |  | Execution |  |  | Monitoring |  |  | Closure
No. | Task / Activity / Deliverable | Project Sponsor | Project Manager | Business Analyst | Tech Lead / Architect | Dev Team | QA / Testing | UX / Design | Change Manager | Finance / Procurement | Legal / Compliance | Operations / Business Owner | External Vendor | PMO | Steering Committee | End User / Customer | Communications | IT Infrastructure | Training & L&D
INITIATION
1 | Approve project business case | A | R | C | [5 empty] | C | C | C |  | I | I
2 | Develop and sign project charter | A | R | C | C |  |  |  |  | C | C | C |  | C | I
3 | Identify and map stakeholders | I | R | R |  |  |  |  | C |  |  | C |  | C | I | C
4 | Appoint project team | A | R |  | C |  |  |  |  | C |  |  |  | I | I
5 | Conduct project kick-off workshop | C | R | R | R | R | R | R | R | C | C | R | C | C | I | C | I | I | I
PLANNING
6 | Develop project management plan | I | R | C | C |  |  |  | C | C | C | C |  | C | I
7 | Define scope and WBS | I | R | R | C | [6 empty] | C |  | C | I | C
8 | Develop project schedule (Gantt) | I | R | C | R | C | [5 empty] | C | C | C | I
9 | Develop budget and cost plan | A | R | C | C |  |  |  |  | R |  | C | C | C | I
10 | Create risk register | I | R | R | R | C |  |  | C | C | C | C | C | C | I
11 | Develop communication plan | C | R | C |  |  |  |  | R |  |  | C |  | C | I | C | R
12 | Procurement planning and tendering | C | C | C | C |  |  |  |  | R | R | C |  | C | I
13 | Resource planning and allocation | I | R | C | R |  |  |  |  | C |  | C |  | C | I
14 | Baseline and sponsor sign-off | A | R |  | C |  |  |  |  | I | I | C |  | I | I
EXECUTION
15 | Manage team and day-to-day delivery | I | R | C | R | R | R | R | C |  |  |  | R | C | I
16 | Stakeholder engagement and comms | C | R | C |  |  |  |  | R |  |  | C | C | C | I | C | R
17 | Requirements gathering and sign-off | I | C | R | C | R |  | R | C |  | C | A |  |  | I | C
18 | Solution design and architecture | I | C | C | R | R |  | C |  |  | C | C | C |  | I | C |  | R
19 | Build / development / implementation | I | C |  | R | R | C | R |  |  |  |  | R |  | I
20 | Testing (SIT, UAT, regression) | I | C | C | R | R | R | C |  |  |  | C | C |  | I | R
21 | Training delivery | I | C | C |  |  |  | R | R |  |  | A |  | C | I | R |  |  | R
MONITORING
22 | Project status reporting | I | R | C | C | C | C |  | C |  |  | C | C | R | I
23 | Risk and issue management | C | R | R | R | C | C |  | C | C | C | C | C | C | I
24 | Change control management | A | R | C | C |  |  |  | C | C | C | C | C | C | I
25 | Budget tracking and reporting | I | R | C | [5 empty] | R |  | C |  | C | I
26 | Quality assurance and audits | I | C | C | R | C | R |  |  |  | C | C | C | C | I | C
CLOSURE
27 | User acceptance and sign-off | C | R | C | C |  | R |  |  |  |  | A |  |  | I | R
28 | Lessons learned session | C | R | R | R | R | R | R | R | C | C | R | C | R | I | C | C | C | C
29 | Project closure report | A | R | C | C |  |  |  | C | C |  | C |  | R | I
30 | Benefits realisation handover | A | R | C |  |  |  |  | C | C |  | R |  | C | I
31
32
33
34
35
36
37
38

## Responsibility Summary
RESPONSIBILITY SUMMARY — WHO DOES WHAT
Use this sheet as a quick-reference summary for each team member's responsibilities. Share with team members at kick-off.
Team Member / Role | R — Responsible For | A — Accountable For | C — Consulted On | I — Informed About
Project Sponsor | Approve business case; Final go/no-go decision | Overall project success and business outcomes | Charter, scope, budget, risks, change requests | Status reports, lessons learned, closure
Project Manager | Day-to-day delivery; Status reporting; Risk management; Schedule management | Project delivery within scope, time and budget | All major project decisions and changes | Steering committee decisions
Business Analyst | Requirements gathering; Process analysis; UAT coordination | Requirements completeness and sign-off | Solution design; Change requests; Testing | Technical architecture decisions
Tech Lead / Architect | Technical design; Solution architecture; Build oversight | Technical quality and architecture decisions | Requirements; Testing strategy; Change requests | Budget and procurement decisions
Development Team | Building, coding and unit testing all deliverables | Code quality and technical delivery | Architecture reviews; Change requests | Business requirements sign-off
QA / Testing | Test planning; System and regression testing; UAT support | Testing quality and defect management | Requirements; Solution design; Change requests | Go-live approval decision
Change Manager | Change management plan; Stakeholder engagement; Training oversight | User adoption and change readiness | Communications; Scope changes; Project planning | Technical design decisions
Finance / Procurement | Budget tracking; Procurement process; Vendor contracts | Financial accuracy and procurement compliance | Budget changes; Vendor selection; Risk register | Status reports; Delivery milestones
Steering Committee | Major investment decisions; Escalated issues and change requests | Strategic direction and programme investment | Status reports; Budget and scope changes | Operational delivery updates
End User / Customer | UAT participation; Feedback and requirements input | Acceptance of delivered solution | Requirements; UAT planning; Training | Project progress and go-live date

## Blank Template
RACI MATRIX — BLANK TEMPLATE ¦ Add your own tasks and team members
RACI KEY: |  | R = Responsible |  | A = Accountable |  | C = Consulted |  | I = Informed
No. | Task / Activity / Deliverable | Team Member 1 | Team Member 2 | Team Member 3 | Team Member 4 | Team Member 5 | Team Member 6 | Team Member 7 | Team Member 8 | Team Member 9 | Team Member 10
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## Instructions
HOW TO USE THIS RACI MATRIX
STEP | WHAT TO DO | DETAIL
1 | Update project details | Click cell A2 in the "RACI Matrix" tab and replace [Project Name], [Name, PMP] and [DD MMM YYYY] with your project information.
2 | Review the pre-filled matrix | 30 tasks across 5 project phases are pre-filled with realistic RACI assignments for 18 common project roles. Review each task — delete, rename or adapt tasks to match your project. The colour coding updates automatically.
3 | Use the Blank Template tab | Go to the "Blank Template" tab to start fresh with your own tasks and team member names. Replace the column headers ("Team Member 1" etc.) with your actual names.
4 | Enter R, A, C or I in each cell | Type R, A, C or I in any role cell — or use the dropdown (click the cell to see the dropdown arrow). The cell will automatically colour: R=Violet, A=Dark, C=Purple, I=Grey.
5 | Check the ONE A rule | Every task must have exactly ONE Accountable (A). If a task has zero or two A's, there will be confusion about who owns the outcome. This is the most common RACI mistake.
6 | Check every task has at least one R | Every task must have at least one Responsible (R) — the person actually doing the work. If no R is assigned, nobody knows who is executing the task.
7 | Avoid assigning C or I to everyone | A RACI matrix where everyone is Consulted or Informed on everything defeats the purpose. Be selective: only mark Consulted if that person's input genuinely changes the output. Only mark Informed if they need the information to do their own job.
8 | Review at team kick-off | Walk through the RACI matrix at the project kick-off workshop — not just distribute it. People who haven't had a chance to question or discuss their assignments are less likely to own them.
9 | Use the Responsibility Summary tab | The "Responsibility Summary" tab gives each role a plain-English summary of what they are responsible for, accountable for, consulted on and informed about. Share this sheet with each team member individually so their responsibilities are unambiguous.
10 | Update throughout the project | If scope changes, team members change or new workstreams are added — update the RACI matrix. An outdated RACI is worse than no RACI because it creates false clarity.
11 | Export for stakeholder packs | Use File > Print > Save as PDF. Set orientation to Landscape and scale to Fit to Page Width. The matrix is formatted to print cleanly on one wide page.
COMMON MISTAKES
| More than one A per task | Having two Accountable people means neither is truly accountable. If there is genuine disagreement, escalate to the sponsor to make the call.
| PM is R and A for everything | The PM should not be Responsible for doing every task — the PM is accountable for delivery but the team does the work. Over-R'ing the PM is a sign the team lacks clarity on their roles.
| Everyone marked C on everything | Consultation should be reserved for people whose input genuinely shapes the output. Too many C's creates bottlenecks and slows down decisions.
| RACI created and never revisited | The RACI matrix is a living document. Review it at major phase gates and whenever team membership changes.
Template from Sikhana Seekho · sikhanaseekho.com/templates/raci-matrix/ · Free to use and share