## Risk Register
PROJECT RISK REGISTER
Project Name: [Enter Project Name] PM: [Name, PMP] Version: 1.0 Date: [DD MMM YYYY]
RISK SCORE = Probability × Impact |  |  | 1–4 → LOW |  | 5–9 → MEDIUM |  | 10–16 → HIGH |  | 17–25 → CRITICAL
Probability Scale |  |  | 1 = Rare (<10%) |  | 2 = Unlikely (10–30%) |  | 3 = Possible (30–60%) |  | 4 = Likely (60–80%) |  | 5 = Almost Certain (>80%)
Impact Scale |  |  | 1 = Negligible |  | 2 = Minor |  | 3 = Moderate |  | 4 = Major |  | 5 = Catastrophic
ID | Category | Risk Description | Risk Owner | Prob (1–5) | Impact (1–5) | Risk Score | Rating | Response Strategy | Response Action | Contingency Plan | Residual Prob | Residual Impact | Residual Score | Status
R-001 | Scope | Requirements not fully defined before development begins, leading to rework and delayed delivery. | Business Analyst | 4 | 4 | 16 | HIGH | Mitigate | Conduct structured requirements workshops in Week 1–2. Require sign-off on requirements document before development commences. | Freeze scope for Sprint 1; defer additional requirements to Phase 2 backlog. | 3 | 2 | 6 | Open
R-002 | Resource | Key technical resource (Lead Developer) leaves the project before completion. | Project Manager | 2 | 5 | 10 | HIGH | Mitigate | Document all technical decisions and code in Confluence. Identify a backup resource and brief them on architecture. | Engage contractor immediately. Activate knowledge transfer protocol. | 2 | 3 | 6 | Open
R-003 | Schedule | Vendor fails to deliver integration API on agreed date, blocking downstream development. | Technical PM | 3 | 4 | 12 | HIGH | Transfer | Include SLA and penalty clause in vendor contract. Weekly milestone check-ins with vendor account manager. | Activate secondary vendor identified in procurement plan. Descope integration to Phase 2. | 2 | 3 | 6 | Open
R-004 | Budget | Project scope expands beyond approved baseline due to stakeholder-driven additions. | Project Manager | 4 | 3 | 12 | HIGH | Avoid | Enforce formal change control from project kick-off. All scope additions require Change Request Form and sponsor approval. | Draw on contingency reserve. Escalate to sponsor if contingency exceeded. | 2 | 2 | 4 | Open
R-005 | Quality | User Acceptance Testing reveals critical defects that require significant rework. | QA Lead | 3 | 4 | 12 | HIGH | Mitigate | Implement continuous integration and automated unit testing from Sprint 1. Conduct informal demos with key users every 2 weeks. | Extend UAT period by 2 weeks. Delay go-live if critical defects unresolved. | 2 | 2 | 4 | Open
R-006 | Stakeholder | Key stakeholder disengaged — slow to provide decisions, feedback or approvals. | Project Manager | 3 | 3 | 9 | MEDIUM | Mitigate | Establish decision SLAs in steering committee terms of reference. Escalate outstanding decisions after 5 business days. | Escalate to sponsor. Document impact of delayed decision formally. | 2 | 2 | 4 | Open
R-007 | Technical | Data migration complexity is underestimated, causing data quality issues at go-live. | Data Architect | 3 | 5 | 15 | HIGH | Mitigate | Commission data audit in Discovery phase. Run full migration rehearsal 4 weeks before go-live. | Delay go-live. Run parallel operation period. Manual data reconciliation if required. | 2 | 3 | 6 | Open
R-008 | External | Regulatory change requires changes to already-built functionality. | Compliance Lead | 2 | 4 | 8 | MEDIUM | Accept | Monitor regulatory announcements monthly. Build configurable rules engine to reduce rework cost. | Activate change request process. Prioritise regulatory fix above other backlog items. | 2 | 3 | 6 | Open
R-009 | Resource | Team burnout due to sustained overtime during build phase. | Project Manager | 3 | 3 | 9 | MEDIUM | Mitigate | Monitor team velocity and overtime weekly. Enforce sustainable pace. Escalate resourcing gaps early. | Bring in additional contractor. Re-baseline timeline if team health at risk. | 2 | 2 | 4 | Open
R-010 | Schedule | Critical path activity delayed due to dependency on another programme not on schedule. | Programme Manager | 3 | 4 | 12 | HIGH | Mitigate | Map all external dependencies in Week 1. Establish weekly dependency forum with all stream leads. | Fast-track parallel activities. Descope dependent feature to Phase 2. | 2 | 3 | 6 | Open
R-011 | Budget | Vendor costs increase mid-project due to out-of-scope requests made without change control. | Project Manager | 3 | 3 | 9 | MEDIUM | Avoid | All vendor requests routed through PM. Change order required for any work outside contract SOW. | Dispute invoice through contract mechanism. Draw on contingency. | 2 | 2 | 4 | Open
R-012 | Technical | Infrastructure capacity insufficient to support go-live user volumes. | Infrastructure Lead | 2 | 5 | 10 | HIGH | Mitigate | Conduct load testing 6 weeks before go-live. Size infrastructure based on 150% of expected peak load. | Emergency capacity request. Staged rollout to reduce load at go-live. | 1 | 3 | 3 | Open
R-013 | Stakeholder | Change resistance from end users leading to low adoption post-go-live. | Change Manager | 4 | 3 | 12 | HIGH | Mitigate | Develop and execute change management and training plan. Champions network in each department. | Extended hypercare period. Additional training sessions. Escalate to business owner. | 2 | 2 | 4 | Open
R-014 | External | Third-party data feed unavailable at go-live due to supplier technical issues. | Integration Lead | 2 | 3 | 6 | MEDIUM | Transfer | Include data feed SLA in supplier agreement. Test data feed in staging environment 4 weeks prior. | Activate manual data entry workaround. Notify affected users. Escalate to supplier. | 1 | 2 | 2 | Open
R-015 | Quality | Go-live timing clashes with business peak period, causing operational disruption. | Project Manager | 2 | 4 | 8 | MEDIUM | Mitigate | Agree go-live blackout windows with business in advance. Buffer 4 weeks before peak period. | Postpone go-live to post-peak window. Maintain current system in parallel. | 1 | 2 | 2 | Closed
R-016 | [5 empty] | 0 | [6 empty] | 0
R-017 | [5 empty] | 0 | [6 empty] | 0
R-018 | [5 empty] | 0 | [6 empty] | 0
R-019 | [5 empty] | 0 | [6 empty] | 0
R-020 | [5 empty] | 0 | [6 empty] | 0
R-021 | [5 empty] | 0 | [6 empty] | 0
R-022 | [5 empty] | 0 | [6 empty] | 0
R-023 | [5 empty] | 0 | [6 empty] | 0
R-024 | [5 empty] | 0 | [6 empty] | 0
R-025 | [5 empty] | 0 | [6 empty] | 0
R-026 | [5 empty] | 0 | [6 empty] | 0
R-027 | [5 empty] | 0 | [6 empty] | 0
R-028 | [5 empty] | 0 | [6 empty] | 0
R-029 | [5 empty] | 0 | [6 empty] | 0
R-030 | [5 empty] | 0 | [6 empty] | 0
TOTAL RISKS |  |  |  | 14 |  | 0 |  | 9 |  | 6 |  | 0

## Risk Matrix
RISK PROBABILITY × IMPACT MATRIX
Risk ID is placed in the corresponding cell based on its Probability (rows) and Impact (columns)
|  | Impact 1 Negligible | Impact 2 Minor | Impact 3 Moderate | Impact 4 Major | Impact 5 Catastrophic
PROBABILITY | 5 – Almost Certain (>80%) | 5 MEDIUM | 10 HIGH | 15 HIGH | 20 CRITICAL | 25 CRITICAL
| 4 – Likely (60–80%) | 4 LOW | 8 MEDIUM | 12 HIGH R-004, R-013 | 16 HIGH R-001 | 20 CRITICAL
| 3 – Possible (30–60%) | 3 LOW | 6 MEDIUM | 9 MEDIUM R-006, R-009, R-011 | 12 HIGH R-003, R-005, R-010 | 15 HIGH R-007
| 2 – Unlikely (10–30%) | 2 LOW | 4 LOW | 6 MEDIUM R-014 | 8 MEDIUM R-008, R-015 | 10 HIGH R-002, R-012
| 1 – Rare (<10%) | 1 LOW | 2 LOW | 3 LOW | 4 MEDIUM | 5 MEDIUM
| LOW (1–4) |  | MEDIUM (5–9) |  | HIGH (10–16) |  | CRITICAL (17–25)

## Instructions
HOW TO USE THIS RISK REGISTER
STEP | WHAT TO DO | DETAIL
1 | Update project details | Click on cell A2 in the "Risk Register" tab and replace [Enter Project Name], [Name, PMP], and [DD MMM YYYY] with your project information.
2 | Review existing risks | 15 example risks are pre-filled across common categories. Review each one — delete irrelevant risks using row deletion, or adapt the descriptions to your project.
3 | Add your own risks | Rows 24–38 are blank and ready for your additional risks. Type in the description, owner, probability and impact. Scores calculate automatically.
4 | Set Probability (1–5) | Use the dropdown in column E. 1=Rare (<10%), 2=Unlikely (10–30%), 3=Possible (30–60%), 4=Likely (60–80%), 5=Almost Certain (>80%).
5 | Set Impact (1–5) | Use the dropdown in column F. 1=Negligible, 2=Minor, 3=Moderate, 4=Major, 5=Catastrophic. Consider impact on scope, schedule, budget, quality AND reputation.
6 | Risk Score auto-calculates | Column G = Probability × Impact. The cell colour automatically updates: Green (Low 1–4), Yellow (Medium 5–9), Orange (High 10–16), Red (Critical 17–25).
7 | Set Response Strategy | Column I dropdown: Avoid (eliminate the risk), Mitigate (reduce probability or impact), Transfer (shift to third party e.g. insurance), Accept (acknowledge and monitor), Escalate (raise to higher authority).
8 | Document Response Actions | Column J: write specific, actionable steps. Who does what by when. Vague responses ('monitor the risk') do not reduce risk exposure.
9 | Set Residual Risk | After response actions, re-score the remaining risk in columns L (Residual Prob) and M (Residual Impact). Column N shows the residual score automatically.
10 | Update Status regularly | Column O dropdown: Open (risk active), In Progress (response underway), Closed (risk passed or fully mitigated), Cancelled (no longer applicable).
11 | Use the Risk Matrix tab | The "Risk Matrix" tab plots all pre-filled risks on a 5×5 heat map. Update it manually when you add or change risks, or use it as a stakeholder communication tool.
12 | Present to stakeholders | Export to PDF using File > Print > Save as PDF. Set orientation to Landscape. The register is formatted to fit on one wide page. Use the Risk Matrix for executive presentations.
TIPS
| Review cadence | Review the risk register at every steering committee and weekly with your team. Risks that are never reviewed are risks that are never managed.
| Top risks report | For executive reporting, filter or extract your top 5–10 risks by score and include in your project status report. Use our free Status Report template.
| Risk owner ≠ PM | Every risk should have a specific owner who is accountable for executing the response plan. The PM is responsible for ensuring owners act — not for doing everything themselves.
| Quantify where possible | Where a risk has a potential financial impact, add a monetary estimate in the description (e.g. 'estimated $50K rework cost if this risk materialises').
Template from Sikhana Seekho · sikhanaseekho.com/templates/risk-register/ · Free to use and share